## Event
Step to be completed | Days Before/ After | Due Date
If OSR is used, submit usage request | -210 | 2022-07-02
Secure Location | -126 | 2022-09-24
Hold Committee Meeting | -126 | 2022-09-24
Submit online calendar and registration request tool | -120 | 2022-09-30
Promote with troops | -119 | 2022-10-01
Hold Committee Meeting, develop program | -91 | 2022-10-29
Develop recognition plan and patch | -91 | 2022-10-29
Physical facilities arranged | -91 | 2022-10-29
Have final budget approved by staff leader | -90 | 2022-10-30
Registration opens | -90 | 2022-10-30
Committee promotes event at roundtables | -90 | 2022-10-30
Committee promotes event at roundtable | -60 | 2022-11-29
NCAP Local Council Authorization | -60 | 2022-11-29
Request PO and order any supplies | -56 | 2022-12-03
Arrange for religious observance | -49 | 2022-12-10
Lay out troop sites and plan assignments | -49 | 2022-12-10
Committee promotes event at roundtable | -30 | 2022-12-29
Prepare any event signs | -28 | 2022-12-31
Develop any special guest list | -28 | 2022-12-31
Arrange for first aid and hospital emergency service | -21 | 2023-01-07
Arrange facilities for Trading Post, PA System, etc., if needed | -14 | 2023-01-14
Complete details for final program bulletin; reproduce and mail | -14 | 2023-01-14
Plan evening program materials and assign responsibilities | -14 | 2023-01-14
Pick - up materials and take to site | -7 | 2023-01-21
Set- up | -1 | 2023-01-27
Hold Event | 0 | 2023-01-28
Hold post-event debrief | 7 | 2023-02-04
Formulas:
Due Date = IF(C27>0,C27+[Days Before/ After]," ")
Note on C27: Insert event date here